Council Plan 2021-25 
quarterly report card

April to June 2024

Contents

Economy of the Future	3

Highlights for quarter four (April to June 2024)	3

Our progress	3

The major initiatives we’re delivering this year	4

How we’re measuring progress over four years	4

Melbourne’s unique identity and place	6

Highlights for quarter three (April to June 2024)	6

Our progress	6

The major initiatives we’re delivering this year	7

How we’re measuring progress over four years	8

Aboriginal Melbourne	9

Highlights for quarter three (April to June 2024)	9

Our progress	9

The major initiatives we’re delivering this year	9

How we’re measuring progress over four years	10

Climate and biodiversity emergency	11

Highlights for quarter three (April to June 2024)	11

Our progress	11

The major initiatives we’re delivering this year	12

How we’re measuring progress over four years	12

Access and affordability	14

Highlights for quarter three (April to June 2024)	14

Our progress	14

The major initiatives we’re delivering this year	15

How we’re measuring progress over four years	16

Safety and wellbeing	17

Highlights for quarter three (April to June 2024)	17

Our progress	18

The major initiatives we’re delivering this year	18

How we’re measuring progress over four years	19

# Economy of the Future

We will focus on driving economic recovery and creating the conditions for a strong, adaptive, sustainable and thriving future city economy supported by a diverse mix of industries and jobs that provide dignity and opportunity.

## Highlights for quarter four (April to June 2024) The Mainstreaming Twilight Trade project ended in May, with webinars and in-person sessions planned to help businesses learn about twilight trading. More than 850 international students were actively involved through various programs, celebrations, and workshops, showcasing the city's commitment to international student engagement. Invest Melbourne has delivered 85 investment projects, creating or expediting 1,209 jobs and $369 million in capital expenditure year to date. The sixth edition of the Melbourne Economy Snapshot, published in June, highlights improving shopfront vacancy rate across the municipality at 10.4 per cent, with the central city retail core experiencing a reduced vacancy rate of 6.5 per cent, Australia's lowest CBD vacancy rate, and growth in the city’s retail and hospitality sectors. The integrated Only in the City campaign drove visitation and spending in winter, with a $15 million increase in visitor spending monthly. Only in the City and What’s On achieved more than 1 million website sessions during the campaign. Hotel occupancy in Melbourne averaged 72 per cent, up 6 per cent year-on-year. Domestic visitor expenditure for the year ending March 2024 was $7.2 billion, a 177 per cent increase on March 2022. The Firelight program was launched, with a new addition to the program called 'Firelight Labyrinth', a 17 day ticketed activation in Docklands. The May Melbourne Conversations event had more than 900 tickets booked with more than 400 people attending the event at Federation Square. The TradeStart program, in partnership with Austrade, successfully concluded on 30 June, having engaged and supported 56 Melbourne-based health companies and completed 106 Austraderecognised export-related services to 32 unique clients in the sector. ## Our progress Delays in finalising funding for The Couch impacted the implementation of the Economic Development Strategy. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Continue to strengthen Melbourne’s economic recovery, including through precinct and shopfront activation, delivery of an enhanced business concierge service and support for the night-time economy. | Deliver | On track |
| Ensure Melbourne is the easiest place to start and grow a business through the establishment of Invest Melbourne. | Deliver | Completed |
| Drive economic growth and resilience by implementing the Economic Development Strategy, focusing support on existing and emerging industry sectors. | Deliver Partner | On track |
| Work in partnership with the Victorian Government and other stakeholders to advocate for and deliver integrated high-quality public and active transport in urban renewal areas. | Partner | On track |
| Establish a new tourism entity called Visit Melbourne and review and refresh the program of City of Melbourne-owned and sponsored events to maximise opportunities to drive visitation and spend. | Deliver Partner | Completed |
| Market and promote Melbourne as a great place to live for all, while ensuring key workers have access to affordable housing. | Deliver | Completed |
| Increase visitation to Docklands by partnering with the Victorian Government and key stakeholders to enable reconstruction and redevelopment in Central Pier and surrounds. | Partner Advocate | On track |
| Review Melbourne’s international relationships to optimise future and existing partnerships to enable mutual growth and opportunity. | Deliver | On track |
| Partner with industry to support the development of globally competitive innovation ecosystems. | Partner Deliver | On track |
| Develop a corporate strategy for the City of Melbourne to drive exemplary customer service, digitise services and operations, improve productivity and identify new revenue opportunities. | Deliver | On track |
| Embed the Sustainable Development Goals in the way City of Melbourne plans, prioritises its investments, reports and benchmarks against other cities. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Capital city gross local product. | Increase |
| Number of businesses in the municipality. | Increase |
| Number of start-ups in the municipality. | Increase |
| Vacancy rate of retail premises. | Decrease |
| Proportion of residents employed in the municipality. | Increase |
| Gross local product per capita per person employed. | Increase |
| Number of jobs in the municipality. | Increase |
| Number of visitors to the municipality. | Increase |
| Planning applications decided within required timeframes. | 100% |

# Melbourne’s unique identity and place

Over the next four years we will celebrate and protect the places, people and cultures that make Melbourne a unique, vibrant and creative city with world-leading liveability.

## Highlights for quarter three (April to June 2024) The Event Partnership Program supported multiple community based events, including the ANZAC Day parade and Dawn Service, a new addition to the Event Partnership Program, which saw almost 50,000 people gather for the dawn service and parade combined. In a major program milestone at the Queen Victoria Market precinct, the removal of the roundabout at the corner of Franklin and Queen Streets has delivered a newly realigned intersection in time for the Southern Development Site handover. The Public Art Advisory Panel endorsed the proposal to create a new public artwork at the 8 Hour Memorial Reserve to commemorate workers who have died at work. The commission is a partnership between City of Melbourne, the Victorian Trades Hall and WorkSafe. The first phases of community engagement for the Miles and Dodds Street Reserve and Chapman Street Reserve expansion projects were completed, and the development of draft concept plans has commenced. Three sold-out Melbourne Design Week events were delivered on the topics of inclusion, material reuse and ecology in urban streetscapes. Progress on priority projects in the Moonee Ponds Creek corridor progressed, including the prioritisation of two active transport crossings in Macaulay for further concept design and costings. ## Our progress Challenges facing the construction sector due to rising costs continue to impact delivery timelines for the Queen Victoria Market Precinct Renewal. There is a high-level of uncertainty regarding property availability in Southbank and urban renewal areas Delivery of our major initiatives within the Council Plan term is on track

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Partner with the Victorian Government and other stakeholders to deliver specific components of Greenline along the north bank of the Yarra River. | Deliver Partner | On track |
| Protect Queen Victoria Market as a traditional open-air market. | Deliver | Delayed |
| Deliver Queen Victoria Market6 precinct improvements and Munro Community Hub. | Deliver Partner | Completed |
| Deliver public art projects that reflect Melbourne’s unique culture and heritage. | Deliver | On track |
| Increase the amount of public open space in the municipality with a focus on areas of greatest need. | Deliver | On track |
| Play a lead role in facilitating the delivery of high-quality and climate adapted urban renewal in Arden and Macaulay, Fishermans Bend, and Docklands in partnership with the Victorian Government. | Partner | On track |
| Facilitate increased investment in unique Melbourne events to further activate and celebrate the city. | Partner | Completed |
| Celebrate, partner and advocate for investment in the city’s three key waterways, the Yarra River-Birrarung, the Maribyrnong and Moonee Ponds Creek. | Partner Advocate | On track |
| Adopt the Municipal Planning Strategy in 2022-23. | Partner | On track |
| Complete heritage reviews and implement associated planning scheme amendments to protect and celebrate heritage in our municipality. | Deliver | On track |
| Champion high quality development and public realm design through delivering the Design Excellence Program. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of residents within 300m of public open space. | Increase |
| Proportion of people surveyed who visit a park in the municipality on a regular basis. | Increase |
| Area of new public open space in Southbank. | 1.1ha (by 2025) |
| Neighbourhoods in the municipality with up-to-date local heritage studies and controls. | 100% |
| Proportion of people who support the city being made up of different cultures. | 100% |
| Value of the creative sector to the local economy. | Increase |
| The number of creative spaces in the municipality. | Increase |
| The number of artists supported by City of Melbourne through city planning, design and city operations. | Increase |
| The number of design reviews of major projects. | Increase |

# Aboriginal Melbourne

For the Wurundjeri, Bunurong, Taungurung, Dja Dja Wurrung and Wadawurrung peoples of the Eastern Kulin, the place now known as Melbourne has always been an important meeting place and location for events of political, cultural, social and educational significance. Over the next four years, we will ensure that First Peoples’ culture, lore, knowledge, and heritage enrich the city’s growth and development.

## Highlights for quarter three (April to June 2024) Shortlisted artists for the Stolen Generation Marker are continuing to develop their concept design for submission to the Working Group. The submission date was extended until mid-June with the working group scheduled to make a decision by the end of June on the selected artist. Continued work on Aboriginal Mapping project, including background research on education resources to inform Traditional Owner consultations. An options paper is being prepared on the development of the app. ‘Truth-telling talks’ - Two events were organised. Blak & Bright about speakers corner and Yalinguth truth telling walk along the Birrarung as part of Open House Melbourne. Council has approved the recommended members for the First Nations Committee. Planning has started for the inaugural meeting. ## Our progress Senior management changes at the traditional owner Corporations have delayed the progress of anannual gathering of the Eastern Kulin. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Explore and deliver opportunities for ‘truth-telling’ to facilitate learning, healing, and change within Melbourne and beyond. This will be an opportunity to impart knowledge of thousands of years of rich history, language and stories, as well as provide a form of restorative justice by acknowledging Aboriginal peoples’ experiences of dispossession and inequity. | Partner | On track |
| Implement the Declaration of Recognition and Commitment in good faith which signals and elevates the City of Melbourne’s shared commitment for reconciliation across the whole of the organisation. | Deliver | Completed |
| Govern with Sovereign First Nations to enable true self-determination, where deliberative engagement is proactive, responsive and consistent. | Deliver | On track |
| Commence planning for a co-designed First Nations Cultural Precinct with First Peoples – a place to retain, maintain and recreate in a culturally specific geography, where First Peoples can practice continuity of customs and traditions, through uninterrupted connection to lands and waters. | Partner | Closed |
| Support a partnership forum – an annual gathering of the Eastern Kulin (noting the history of Tanderrum). | Partner | Closed |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of people surveyed who demonstrate an understanding of Melbourne’s Aboriginal heritage and culture. | 100% |
| Proportion of people surveyed who believe the relationship with Aboriginal people is important. | 100% |
| Delivery of the City of Melbourne’s Reconciliation Action Plan. | 100% |
| Level of involvement of Traditional Custodians in city governance. | Increase |

# Climate and biodiversity emergency

Over the next four years, we will prioritise our environment and take urgent action to reduce emissions and waste in order to protect public health, strengthen the economy and create a city that mitigates and adapts to climate change. The City of Melbourne declared a climate and biodiversity emergency in 2019.

## Highlights for quarter three (April to June 2024) The Council of Capital Cities Lord Mayor's Climate Action Working Group met in person to develop a new plan for 2024-2025. Focuses for the year ahead will be advocacy to the federal government on electrifying buildings, funding urban resilience projects and electric buses. Preparations continued with the Urban Land Institute in bringing together an international panel of experts on sustainable precinct uplift. The experts gathered in Melbourne in June to propose a path forward for Retrofit Melbourne's Precinct initiative. Melbourne has been selected to pilot a new C40 Cities Climate Transition Framework, which will be adopted globally in 2025. Our participation in the pilot will ensure that we are well prepared to continue our leadership on climate. The renewal of the urban forest precinct plans to deliver our urban forest strategy goals over the next ten years is on track. Community engagement is complete for East Melbourne, South Yarra, Central City, Kensington, North and West Melbourne and Docklands. Research into best practice behaviour change for waste education has commenced. This will inform a food and organic waste education campaign in 2024-25. The Power Melbourne project delivered the Council House battery, with batteries at The Boyd Community Hub and Library at the Dock batteries being on track. ## Our progress Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| To enhance Melbourne’s position as a global leader on climate action, we will undertake bold advocacy on behalf of our community. | Deliver | On track |
| Create an enabling environment for Melbourne businesses and universities to become the employment centre of a resilient zero-carbon economy. | Deliver | On track |
| Progress a planning scheme amendment to improve the environmental performance of buildings in order to reduce emissions to zero by 2040. | Deliver Partner | On track |
| Deliver on our Urban Forest Strategy including tree canopy, private greening incentives and city greening. | Partner | On track |
| Lead the reduction of food waste and diversion of waste from landfill, by continuing the Food Organics, Green Organics rollout through high-rise apartment innovation and by addressing food-waste reduction. | Deliver Partner | On track |
| Support the development of a circular economy through bold leadership and community neighbourhood projects, including the container deposit scheme, alternative waste technologies, circular economy guidelines and partnered or aggregated demand to stimulate end markets. | Deliver | On track |
| Support the development of battery storage and renewable energy in the municipality through the Power Melbourne initiative. | Partner Advocate | On track |
| Implement the Climate and Biodiversity Emergency action plan. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Municipal greenhouse gas emissions. | 33% reduction (from 2015 baseline by 2025) |
| On-road transport emissions. | Decrease |
| Installed battery storage capacity in the municipality. | Increase |
| Household waste produced. | 10% reduction (by 2025) |
| Municipal waste diverted from landfill. | 50% increase (by 2025) |
| Alternative water use. | Increase |
| Stormwater quality. | Increase |
| Hospital admissions in relation to extreme weather events. | Decrease |
| Percentage of tree canopy cover in the public realm. | 27% (by 2025) |
| Number of trees planted in the municipality. | 2400 plus number of trees removed in previous year, or 3000, whichever is more. |
| Area of native understorey habitat in the public realm. | Increase |

# Access and affordability

Over the next four years, we will reduce economic and social inequality by ensuring universal access to housing, core services and information.

## Highlights for quarter three (April to June 2024) - Community consultation on the draft Recreation Facilities Provision Framework commenced, this incorporates a prioritisation framework to guide strategic planning for facility provision including increasing capacity, redevelopment of existing, and provision of new facilities. - Demolition of the old Ryder Pavilion occurred with construction of the new Ryder Pavilion commencing in May, the turning of the sod was marked by a site visit from the Lord Mayor and Councillor Griffiths. - An event was held at Make Room to celebrate the completion of the first apartment and to announce cohealth as the onsite service support partner. Donors and key project partners had the opportunity to view the progress and learn more about the service support model. - Companion services were provided by Travellers Aid at the Comedy Festival, Walk in the Park, Anzac Day, the Australian Network on Disability Impact Conference and The Long Walk. - Five members of the Disability Advisory Committee participated in a Greenline Precinct Plan workshop to explore and provide advice on specific design elements such as signage, wayfinding, surfaces, materials, amenities, lighting and safety along the river’s edge. - Discussions on the furniture layout, artwork and wayfinding for City Library are progressing. Work on the curated collection for the library branch is complete, with repurposed items redistributed throughout the library network and donations made to various community organisation - Up to May 2024, three Foodbank Farms to Families food truck events were held, which were attended by a total of 930 community members. During these events, 5,650 kilos of fresh fruit and vegetables were distributed. About 75% of the attendees were residents of the municipality, with 235 residents coming from a CBD address. Additionally, 362 people, representing over half of the total respondents, reported being referred from City of Melbourne services such as family services, neighbourhood partners, the Couch, or libraries. ## Our progress Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Increase and upgrade accessible, inclusive spaces for women in City of Melbourne sports facilities | Deliver | On track |
| Implement a neighbourhood model by working with communities to develop neighbourhood plans and neighbourhood service centres that respond to the local community’s existing and projected needs. | Deliver | On track |
| Deliver a revitalised library network, including pop-up libraries, to increase access for our diverse community and to help revitalise the city. | Deliver | On track |
| Deliver the Disability Access Plan 2020–2024 including ensuring our services and events are more accessible, increasing the number of accessible adult change facilities, and partnering with community and transport groups to make transport more accessible. | Deliver Partner | Completed |
| Develop and deliver initiatives and programs that will provide food relief to vulnerable members of our community and improve local food production by supporting communities to grow their own food. | Deliver Partner Advocate | On track |
| As part of a new corporate strategy for the City of Melbourne, ensure our core services remain accessible and affordable. | Deliver | On track |
| In partnership with the Victorian Government commence construction on a replacement North Melbourne Community Centre precinct for the Melrose St community and growing Macaulay population. | Deliver Partner | On track |
| Deliver programs that will build digital literacy skills and capabilities, improve access to free Wi-Fi from our community facilities and advocate for appropriate digital infrastructure, to improve digital inclusion for all, particularly for vulnerable groups. | Deliver | On track |
| Create a new entity ‘Homes Melbourne’, to coordinate and facilitate more affordable housing for key workers and people on low-incomes and progress a demonstration project on Council-owned land, support the Make Room accommodation project and new homeless support hubs for vulnerable citizens to access essential support. | Partner | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Number of people sleeping rough who have not been offered accommodation. | Zero |
| Number of people supported through a range of accommodation including long-term supportive housing and affordable housing. | 500 (by 2025) |
| Number of new demonstration social and affordable housing units facilitated on City of Melbourne land. | 100 (by 2025) |
| Proportion of people reporting food insecurity. | 25% reduction (by 2025) |
| Proportion of people surveyed who participate in lifelong learning in the municipality. | Increase |
| Proportion of people surveyed who participate in arts and cultural activities in the municipality. | Increase |

# Safety and wellbeing

Over the next four years, we will plan and design for the safety and wellbeing of those who live, visit, work and do business in Melbourne, regardless of their background.

## Highlights for quarter three (April to June 2024) - In partnership with Melbourne Water, three Flood Education Sessions were delivered in Kensington and West Melbourne. - The High Life Expo was held on 1 June with approximately 700 people attending to learn about making apartment living more sustainable and resilient. - The Sandridge Bridge was repainted, colour matched and all graffiti removed, vastly improving the amenity along Southbank Promenade. - City of Melbourne and Yarra Trams have installed anti-graffiti film on every tram glass panel in the Central City. The film was installed on all eight ‘super stops’ owned by CoM to create uniform improvement across the entire City. The film is resistant to stealth marker corrosive ink and any graffiti can be wiped from the surface instantly. - Work has been underway to establish a partnership with an Aboriginal Controlled Community Organisation to provide the first family violence support outpost and safe space specifically for Aboriginal women and their children within the City of Melbourne. In May, Carlton Baths Family Services was identified as the preferred site to pilot the outpost for a 6-month period commencing July 2024. - VicRoads bike counters show strong growth in volumes. 349,304 bikes were recorded in April 2024 compared to 253,433 in April 2022 – an increase of 38%. The St Kilda Rd site recorded the most bikes with 58,065 counted in April. - Projects continued as part of the implementation of Transport Strategy 2030 included: - Grattan Street bike lanes completed between Bouverie and Drummond Streets. - Streetscape upgrades on Exhibition Street continue. A plaza area is being constructed outside Her Majesty’s Theatre, along with separated bike lanes and a drop-off/pick-up area. - Speed Limit changes delivered on the CBD Little Streets as a trial during covid are being formalised. “20Km/h Shared Zone” signage is being replaced with “20km/h” speed limit signage. Other permanent upgrades of temporary infrastructure will follow. - Safety improvements adjacent to Docklands Primary school are complete, involving upgraded paths that provide separation between people walking and riding bikes. ## Our progress Limited access to sites and development of alternative design options have resulted in delays to some pedestrian and bicycle infrastructure projects. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Continue to implement the Transport Strategy 2030, including delivery of a protected bike lane network, station precincts, streets for people, safer speed limits, etcetera. | Advocate Partner Deliver | On track |
| Deliver the North and West Melbourne and Docklands Transport and Amenity Program in partnership with the Victorian Government. | Deliver Partner | Delayed |
| City of Melbourne will design and deliver the upgrades to the City Road northern undercroft by end of 2023-2024 and advocate for the full delivery of upgrades to the City Road East and West. | Deliver Advocate | Delayed |
| Adopt in 2021-22 and then implement an Inclusive Melbourne Strategy that will increase access to opportunities for all people who live, work, study in and visit the city. | Deliver | On track |
| We will be a leading organisation on equality and inclusion and deliver programs in communities that will reduce physical and psychological harm to all people. | Deliver | Completed |
| We will continue to work with Victoria Police and other agencies to deliver a range of initiatives that improve safety on the streets of Melbourne and within our communities. | Partner Deliver | On track |
| Deliver and maintain a clean city through the Rapid Response Clean Team initiative. | Deliver | On track |
| Engage and prepare residents and communities to enhance their resilience to hazards, disasters and the health impacts of climate change. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of people who report feeling safe in the city. | 90% by day, 65% by night |
| Melburnians’ self-reported sense of belonging to community. | At least 70 /100 |
| Rate of recorded family violence incidents. | Decrease |
| Complaints of discrimination based on sexual orientation, sexuality, disability, sex, gender, race, religious or political beliefs or other grounds for unlawful discrimination. | Decrease |
| Proportion of adults who get adequate physical exercise. | Increase |
| Rate of ambulance attendance for alcohol and drug misuse in the municipality. | Decrease |
| Number of transport related injuries and fatalities. | Decrease |
| Proportion of trips made by public transport, bicycle or on foot. | Increase |

https://www.melbourne.vic.gov.au/business/Pages/business-concierge-service.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/Pages/economic-development-strategy-2031.aspx

https://www.melbourne.vic.gov.au/arts-and-culture/strategies-support/funding/Pages/event-partnership-program.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/Pages/united-nations-sustainable-development-goals.aspx

https://participate.melbourne.vic.gov.au/greenline/implementation-plan-overview

https://www.melbourne.vic.gov.au/qvmrenewal

https://participate.melbourne.vic.gov.au/arden/plan

https://participate.melbourne.vic.gov.au/macaulay-refresh

https://www.fishermansbend.vic.gov.au

https://participate.melbourne.vic.gov.au/city-river-strategy

https://participate.melbourne.vic.gov.au/design-excellence-program

https://www.melbourne.vic.gov.au/community/greening-the-city/urban-forest/pages/urban-forest-strategy.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/eco-city/climate-change/Pages/taking-action-climate-change.aspx?k=climate+and+biodiversity+emergency&type=web

https://participate.melbourne.vic.gov.au/disability-access-plan

https://www.melbourne.vic.gov.au/parking-and-transport/transport-planning-projects/Pages/transport-strategy.aspx

https://participate.melbourne.vic.gov.au/inclusive-melbourne-strategy