Council Plan 2021-25 
quarterly report card

July to September 2024

Contents

Economy of the Future	3

Highlights for quarter one (July to September 2024)	3

Our progress	3

The major initiatives we’re delivering this year	4

How we’re measuring progress over four years	5

Melbourne’s unique identity and place	6

Highlights for quarter one (July to September 2024)	6

Our progress	6

The major initiatives we’re delivering this year	8

How we’re measuring progress over four years	9

Aboriginal Melbourne	10

Highlights for quarter one (July to September 2024)	10

Our progress	10

The major initiatives we’re delivering this year	10

How we’re measuring progress over four years	11

Climate and biodiversity emergency	12

Highlights for quarter one (July to September 2024)	12

Our progress	13

The major initiatives we’re delivering this year	14

How we’re measuring progress over four years	15

Access and affordability	16

Highlights for quarter one (July to September 2024)	16

Our progress	16

The major initiatives we’re delivering this year	17

How we’re measuring progress over four years	18

Safety and wellbeing	19

Highlights for quarter one (July to September 2024)	19

Our progress	20

The major initiatives we’re delivering this year	20

How we’re measuring progress over four years	21

# Economy of the Future

We will focus on driving economic recovery and creating the conditions for a strong, adaptive, sustainable and thriving future city economy supported by a diverse mix of industries and jobs that provide dignity and opportunity.

## Highlights for quarter one (July to September 2024) The Small Business Grants Program received significant interest with 370 applications totalling $7.88 million in requests across four streams. A roundtable with hospitality businesses identified key support areas: safety, marketing, city disruption, and patronage. Draft roadmaps for the hospitality and music sectors will be circulated in December 2024. The Melbourne Economy Snapshot in September focused on twilight trading, aiding retailers with industry data. Future updates will be posted after the caretaker period. Precinct associations received $881,200 in funding, with individual amounts to be shared on the Council’s website after the caretaker period. Melbourne's Economic Development Strategy is progressing, and key stakeholder interviews are underway for a program review by SGS Economics, with a report due in November. Employability outcomes for international students have been enhanced through a paid internship program involving over 1,400 students. Development is ongoing for separated bike lanes on Arden Street and preparations for the Fishermans Bend Standing Advisory Committee. Revitalisation of Central Pier Waterfront includes activations for Wurundjeri Woiwurrung culture, landscaping, and major civic spaces. Melbourne’s global connections were strengthened through initiatives like the 2024 NexStar program connecting international students with Chinese technology firms and hosting a panel on India’s growing digital gaming industry. The She Loves Tech competition was held in Melbourne, empowering women-led tech startups, with the winner representing Oceania in Singapore. ## Our progress With central pier being a state-owned asset, there will be limited ability for the City of Melbourne to influence the outcome of Development Victoria’s "Revitalising Central Pier Waterfront - Vision and Place Principles". Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Continue to strengthen Melbourne’s economic recovery, including through precinct and shopfront activation, delivery of an enhanced business concierge service and support for the night-time economy. | Deliver | On track |
| Ensure Melbourne is the easiest place to start and grow a business through the establishment of Invest Melbourne. | Deliver | Completed |
| Drive economic growth and resilience by implementing the Economic Development Strategy, focusing support on existing and emerging industry sectors. | Deliver Partner | On track |
| Work in partnership with the Victorian Government and other stakeholders to advocate for and deliver integrated high-quality public and active transport in urban renewal areas. | Partner | On track |
| Establish a new tourism entity called Visit Melbourne and review and refresh the program of City of Melbourne-owned and sponsored events to maximise opportunities to drive visitation and spend. | Deliver Partner | Completed |
| Market and promote Melbourne as a great place to live for all, while ensuring key workers have access to affordable housing. | Deliver | Completed |
| Increase visitation to Docklands by partnering with the Victorian Government and key stakeholders to enable reconstruction and redevelopment in Central Pier and surrounds. | Partner Advocate | On track |
| Review Melbourne’s international relationships to optimise future and existing partnerships to enable mutual growth and opportunity. | Deliver | On track |
| Partner with industry to support the development of globally competitive innovation ecosystems. | Partner Deliver | On track |
| Develop a corporate strategy for the City of Melbourne to drive exemplary customer service, digitise services and operations, improve productivity and identify new revenue opportunities. | Deliver | On track |
| Embed the Sustainable Development Goals in the way City of Melbourne plans, prioritises its investments, reports and benchmarks against other cities. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Capital city gross local product. | Increase |
| Number of businesses in the municipality. | Increase |
| Number of start-ups in the municipality. | Increase |
| Vacancy rate of retail premises. | Decrease |
| Proportion of residents employed in the municipality. | Increase |
| Gross local product per capita per person employed. | Increase |
| Number of jobs in the municipality. | Increase |
| Number of visitors to the municipality. | Increase |
| Planning applications decided within required timeframes. | 100% |

# Melbourne’s unique identity and place

Over the next four years we will celebrate and protect the places, people and cultures that make Melbourne a unique, vibrant and creative city with world-leading liveability.

## Highlights for quarter one (July to September 2024) Community consultation for the Greenline Project took place between July and September 2024, with 660 people participating. The Birrarung Marr precinct work began in April 2024, with consents for main construction works nearing completion. The Birrarung Trial Floating Wetlands have been completed, with maintenance, monitoring, and additional funding secured to expand the trial for another year. Several other city projects are advancing, such as the excavation of the new Trader Shed, which will house essential market infrastructure, including storage and waste management facilities. Plans for Market Buildings and Queen Street public realm upgrades are progressing, with further community engagement on Market Square scheduled. The Bedford Street Pocket Park is expected to be completed by October 2024. Open space projects continue to move forward, including Chelmsford Street Open Space, Miles and Dodds Street Reserve expansion, and Chapman Street Reserve. The Royal Park Master Plan will be released for community engagement later in 2024. Feasibility and design investigations for the Normanby Road Reserve and Errol Street median expansion are also in development, along with preparations for the Swanston Street Triangle landscape construction. The Macaulay Structure Plan, first introduced in 2021, continues with community center planning and Chelmsford Street Open Space development. In Fishermans Bend, the Victorian Government confirmed rail station locations, and Development Victoria is leading the Innovation Precinct’s planning and delivery. The city is also working with the Victorian Government to advance the Arden precinct, with bike lane construction on Arden Street underway. Amendment C432, aimed at updating the Municipal Planning Strategy, was authorised in July 2024 and placed on public exhibition. A review of local planning scheme controls is underway, with further amendments planned. The Design Excellence Advisory Committee is progressing initiatives like the "Places for People" study and new competitions for design excellence, including projects at Queens Corner Building and Queensbridge Square. Heritage and urban design policies are being reviewed, with substantial progress on heritage assessments and updates to the planning scheme. The final Heritage Strategy is expected to be delivered in 2025. Additionally, the Melbourne Design Review Panel has provided input on open space projects, and dynamic conversations about design excellence. ## Our progress Challenges facing the construction sector due to rising costs continue to impact delivery timelines for the Queen Victoria Market Precinct Renewal. Delivery of our major initiatives within the Council Plan term is on track

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Partner with the Victorian Government and other stakeholders to deliver specific components of Greenline along the north bank of the Yarra River. | Deliver Partner | On track |
| Protect Queen Victoria Market as a traditional open-air market. | Deliver | Delayed |
| Deliver Queen Victoria Market6 precinct improvements and Munro Community Hub. | Deliver Partner | Completed |
| Deliver public art projects that reflect Melbourne’s unique culture and heritage. | Deliver | On track |
| Increase the amount of public open space in the municipality with a focus on areas of greatest need. | Deliver | On track |
| Play a lead role in facilitating the delivery of high-quality and climate adapted urban renewal in Arden and Macaulay, Fishermans Bend, and Docklands in partnership with the Victorian Government. | Partner | On track |
| Facilitate increased investment in unique Melbourne events to further activate and celebrate the city. | Partner | On track |
| Celebrate, partner and advocate for investment in the city’s three key waterways, the Yarra River-Birrarung, the Maribyrnong and Moonee Ponds Creek. | Partner Advocate | On track |
| Adopt the Municipal Planning Strategy in 2022-23. | Partner | On track |
| Complete heritage reviews and implement associated planning scheme amendments to protect and celebrate heritage in our municipality. | Deliver | Delayed |
| Champion high quality development and public realm design through delivering the Design Excellence Program. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of residents within 300m of public open space. | Increase |
| Proportion of people surveyed who visit a park in the municipality on a regular basis. | Increase |
| Area of new public open space in Southbank. | 1.1ha (by 2025) |
| Neighbourhoods in the municipality with up-to-date local heritage studies and controls. | 100% |
| Proportion of people who support the city being made up of different cultures. | 100% |
| Value of the creative sector to the local economy. | Increase |
| The number of creative spaces in the municipality. | Increase |
| The number of artists supported by City of Melbourne through city planning, design and city operations. | Increase |
| The number of design reviews of major projects. | Increase |

# Aboriginal Melbourne

For the Wurundjeri, Bunurong, Taungurung, Dja Dja Wurrung and Wadawurrung peoples of the Eastern Kulin, the place now known as Melbourne has always been an important meeting place and location for events of political, cultural, social and educational significance. Over the next four years, we will ensure that First Peoples’ culture, lore, knowledge, and heritage enrich the city’s growth and development.

## Highlights for quarter one (July to September 2024) On 4 July 2024, the Stolen Generations Marker Working Group selected Maree Clarke's design as the preferred concept. A contract was signed, and Clarke held an inception meeting with the group. Her selection was publicly announced on 16 September 2024, with design refinements underway based on feedback. Discussions have begun with the Moomba team to activate the Marker during the festival. For truth-telling events, scoping has started, including work with Melbourne Conversations. On 19 September, a "Yalinguth by the Birrarung" event was held during Riverfest, where Elder Jason Timaru led a tour of Aboriginal heritage along the Yarra River. The "Mapping Aboriginal Melbourne" project is in its scoping phase, working with Traditional Owners to create educational resources. The inaugural meeting of the First Nations Committee took place on 21 August 2024. Discussions with the Wurundjeri Woi-wurrung Cultural Heritage Aboriginal Corporation and Bunurong Land Council continue toward a memorandum of understanding. The first part of the Traditional Owner and Aboriginal Community Engagement Framework is complete, with a briefing paper released in July.. ## Our progress Due to competing demands on Traditional Owner time, the development of a partnership will take longer than anticipated with Wurundjeri. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Explore and deliver opportunities for ‘truth-telling’ to facilitate learning, healing, and change within Melbourne and beyond. This will be an opportunity to impart knowledge of thousands of years of rich history, language and stories, as well as provide a form of restorative justice by acknowledging Aboriginal peoples’ experiences of dispossession and inequity. | Partner | On track |
| Implement the Declaration of Recognition and Commitment in good faith which signals and elevates the City of Melbourne’s shared commitment for reconciliation across the whole of the organisation. | Deliver | Completed |
| Govern with Sovereign First Nations to enable true self-determination, where deliberative engagement is proactive, responsive and consistent. | Deliver | Delayed |
| Commence planning for a co-designed First Nations Cultural Precinct with First Peoples – a place to retain, maintain and recreate in a culturally specific geography, where First Peoples can practice continuity of customs and traditions, through uninterrupted connection to lands and waters. | Partner | Closed |
| Support a partnership forum – an annual gathering of the Eastern Kulin (noting the history of Tanderrum). | Partner | Closed |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of people surveyed who demonstrate an understanding of Melbourne’s Aboriginal heritage and culture. | 100% |
| Proportion of people surveyed who believe the relationship with Aboriginal people is important. | 100% |
| Delivery of the City of Melbourne’s Reconciliation Action Plan. | 100% |
| Level of involvement of Traditional Custodians in city governance. | Increase |

# Climate and biodiversity emergency

Over the next four years, we will prioritise our environment and take urgent action to reduce emissions and waste in order to protect public health, strengthen the economy and create a city that mitigates and adapts to climate change. The City of Melbourne declared a climate and biodiversity emergency in 2019.

## Highlights for quarter one (July to September 2024) Research on financial models for long-term funding of resilience projects has been completed, with advocacy for federal government support underway. The next step is building partnerships with the insurance and financial sectors in early 2025. The Youth Climate Action Grants were awarded in September, supporting youth-led climate projects. Advocacy on mandatory climate reporting and building emissions standards is progressing, with potential federal policy adoption. The Melbourne Climate Network (MCN) has grown to over 500 members, hosting events like the Climate Investor Forum and partnering with the University of Melbourne on climate leadership. MCN's online presence has expanded, and its governance has shifted to focus on corporate engagement. In August, the Sustainable Building Design Amendment C376 was presented at a two-day Victorian Planning Panel Hearing. The Urban Land Institute provided a final report on a zero-carbon precinct, with recommendations under evaluation. City of Melbourne also supported the expansion of the Commercial Building Disclosure Act, requesting biannual disclosures, and completed a desktop study on global regulatory schemes for Retrofit Melbourne. The Urban Forest Strategy is on track, with planning for next year’s tree planting season underway. Urban forest precinct plans are being developed for several areas, with draft plans prepared for Kensington, North and West Melbourne, and Docklands. Community consultations for Southbank, Parkville, and Fishermans Bend are in progress. A waste reduction and recycling education campaign is in development, awaiting finalisation of the Victorian Government's Household Waste and Recycling Service Standard. Plans for a high-rise food organics recycling service and a glass recycling service are also progressing, with implementation plans expected by the end of October 2024. Work on the Kensington Circular Economy Precinct is ongoing, and recruitment of businesses in North and West Melbourne has begun. Batteries for renewable energy storage have been installed at CH1 and Boyd, with commissioning expected by November 2024, though fire mitigation requirements have caused delays. A third battery at Library at the Dock is scheduled for operation by February 2025. City of Melbourne is also awaiting federal funding approval to release a tender for upgrades at Carlton Baths and North Melbourne Recreation Centre. The City of Melbourne is updating street cleaning and graffiti removal contracts to require EV fleet reporting and aims to transition its corporate fleet, currently at 50.8% EVs ## Our progress No significant issues have impacted on our progress this quarter towards meeting our target outcomes.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| To enhance Melbourne’s position as a global leader on climate action, we will undertake bold advocacy on behalf of our community. | Deliver | On track |
| Create an enabling environment for Melbourne businesses and universities to become the employment centre of a resilient zero-carbon economy. | Deliver | On track |
| Progress a planning scheme amendment to improve the environmental performance of buildings in order to reduce emissions to zero by 2040. | Deliver Partner | On track |
| Deliver on our Urban Forest Strategy including tree canopy, private greening incentives and city greening. | Partner | On track |
| Lead the reduction of food waste and diversion of waste from landfill, by continuing the Food Organics, Green Organics rollout through high-rise apartment innovation and by addressing food-waste reduction. | Deliver Partner | On track |
| Support the development of a circular economy through bold leadership and community neighbourhood projects, including the container deposit scheme, alternative waste technologies, circular economy guidelines and partnered or aggregated demand to stimulate end markets. | Deliver | On track |
| Support the development of battery storage and renewable energy in the municipality through the Power Melbourne initiative. | Partner Advocate | Delayed |
| Implement the Climate and Biodiversity Emergency action plan. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Municipal greenhouse gas emissions. | 33% reduction (from 2015 baseline by 2025) |
| On-road transport emissions. | Decrease |
| Installed battery storage capacity in the municipality. | Increase |
| Household waste produced. | 10% reduction (by 2025) |
| Municipal waste diverted from landfill. | 50% increase (by 2025) |
| Alternative water use. | Increase |
| Stormwater quality. | Increase |
| Hospital admissions in relation to extreme weather events. | Decrease |
| Percentage of tree canopy cover in the public realm. | 27% (by 2025) |
| Number of trees planted in the municipality. | 2400 plus number of trees removed in previous year, or 3000, whichever is more. |
| Area of native understorey habitat in the public realm. | Increase |

# Access and affordability

Over the next four years, we will reduce economic and social inequality by ensuring universal access to housing, core services and information.

## Highlights for quarter one (July to September 2024) The City of Melbourne is enhancing inclusive sports facilities for women and girls through new constructions, upgrades, and programming. The Ryder Pavilion in Royal Park is progressing, and the Kensington Community Aquatic and Recreation Centre will be completed by 2025, featuring inclusive changing facilities and women-only programming. In August 2024, the Council endorsed a Recreation Facilities Provision Framework and a Fair Access Policy, ensuring equitable access through 24 specific actions, including a Fair Access application process for community sporting grounds. The Neighbourhood Volunteer Program has launched to promote civic participation among underrepresented communities, with 24 participants selected from diverse backgrounds. The program will be piloted in Carlton, CBD, Docklands, and Southbank. 14 pre-engagement Knowledge Bank reports have been developed to guide City of Melbourne projects, and 27 neighbourhood grants have been awarded for community-led initiatives. Business engagement workshops have commenced, and the place-based focus for the Business Concierge has begun with library sessions and on-street engagement. Democracy Champion pop-ups were held to boost participation in the 2024 local government elections, targeting groups that face barriers to the democratic process, including international students and small businesses. City of Melbourne is working with Queen Victoria Market traders to redirect surplus food to food relief providers, exploring changes in customer demands and operations. Initiatives like the Kensington Fresh Food Market and Seed Libraries encourage fresh food sharing and sustainable gardening. The Kensington market, for example, harvested 50 kilograms of food, with $300 in donations supporting the market. The FareShare program has distributed over 2,500 free meals at the Kathleen Syme Library since July 2024, with no library card required. Additionally, service profiles are being incorporated into the 2025-26 Annual Planning and Budgeting cycle to align community needs with future planning. ## Our progress Further work is being undertaken on the future approach to service planning for City of Melbourne core services under the corporate strategy. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Increase and upgrade accessible, inclusive spaces for women in City of Melbourne sports facilities | Deliver | Delayed |
| Implement a neighbourhood model by working with communities to develop neighbourhood plans and neighbourhood service centres that respond to the local community’s existing and projected needs. | Deliver | On track |
| Deliver a revitalised library network, including pop-up libraries, to increase access for our diverse community and to help revitalise the city. | Deliver | On track |
| Deliver the Disability Access Plan 2020–2024 including ensuring our services and events are more accessible, increasing the number of accessible adult change facilities, and partnering with community and transport groups to make transport more accessible. | Deliver Partner | Completed |
| Develop and deliver initiatives and programs that will provide food relief to vulnerable members of our community and improve local food production by supporting communities to grow their own food. | Deliver Partner Advocate | Delayed |
| As part of a new corporate strategy for the City of Melbourne, ensure our core services remain accessible and affordable. | Deliver | Delayed |
| In partnership with the Victorian Government commence construction on a replacement North Melbourne Community Centre precinct for the Melrose St community and growing Macaulay population. | Deliver Partner | On track |
| Deliver programs that will build digital literacy skills and capabilities, improve access to free Wi-Fi from our community facilities and advocate for appropriate digital infrastructure, to improve digital inclusion for all, particularly for vulnerable groups. | Deliver | On track |
| Create a new entity ‘Homes Melbourne’, to coordinate and facilitate more affordable housing for key workers and people on low-incomes and progress a demonstration project on Council-owned land, support the Make Room accommodation project and new homeless support hubs for vulnerable citizens to access essential support. | Partner | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Number of people sleeping rough who have not been offered accommodation. | Zero |
| Number of people supported through a range of accommodation including long-term supportive housing and affordable housing. | 500 (by 2025) |
| Number of new demonstration social and affordable housing units facilitated on City of Melbourne land. | 100 (by 2025) |
| Proportion of people reporting food insecurity. | 25% reduction (by 2025) |
| Proportion of people surveyed who participate in lifelong learning in the municipality. | Increase |
| Proportion of people surveyed who participate in arts and cultural activities in the municipality. | Increase |

# Safety and wellbeing

Over the next four years, we will plan and design for the safety and wellbeing of those who live, visit, work and do business in Melbourne, regardless of their background.

## Highlights for quarter one (July to September 2024) The City of Melbourne has made progress across various urban and community development projects. In September, the Council endorsed the final Strategic Opportunities Plan for Racecourse Road, signalling further improvements to bike lanes and public spaces. The Northern Undercroft project is advancing, with community engagement completed in June and two potential funding opportunities identified. A report was presented to the Future Melbourne Committee in August, outlining the program's status and potential funding options. In September, the Council approved the Inclusive Melbourne Action Plan 2024-26, which includes 46 targeted actions to improve outcomes for women, people with disabilities, multicultural communities, and LGBTIQA+ individuals. Key initiatives include launching the Elizabeth Morgan House Aboriginal Women’s Family Violence Service and offering gender equity training for City of Melbourne staff. Street safety initiatives have expanded, including the Safe City Cameras program and laneway lighting improvements on Elizabeth Street South. A data dashboard has been created to monitor safety metrics such as crime, graffiti, and rubbish. The Rapid Response Clean Team, which became a permanent service in April 2024, has removed over 1,200 tonnes of waste and 36,500 square meters of graffiti since the beginning of the financial year. The Youth Engagement Program has been successfully delivered to local primary schools, with overwhelmingly positive feedback from students and teachers. This program educates young people about the social impacts of graffiti and has additional sessions scheduled for later in the year. Meanwhile, the Prepared Communities initiative launched in August, focusing on building resilience through education and grants for community projects. The Community Cool Places and Services Grants, which opened in September, offer up to $5,000 to support local organisations in managing heat risks over the summer. Project scoping for the Inclusive Communications Strategy is underway, alongside ongoing efforts by the Co-Chief Heat Officers to engage the community on heat-related risks. These initiatives aim to bolster resilience and inclusivity within the city, ensuring long-term sustainability and community wellbeing. ## Our progress Additional traffic modelling required by the Department of Transport and Plannings has impacted the Hawke Street Linear Park and Spencer Street North Master Plan, which are currently on hold. Delays in public art allocations have affected the Franklin Street upgrade, but work continues on its streetscape improvements. The Northern Undercroft has been delayed due to a lack of secured funding, particularly for City Road West and East upgrades Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Continue to implement the Transport Strategy 2030, including delivery of a protected bike lane network, station precincts, streets for people, safer speed limits, etcetera. | Advocate Partner Deliver | On track |
| Deliver the North and West Melbourne and Docklands Transport and Amenity Program in partnership with the Victorian Government. | Deliver Partner | Delayed |
| City of Melbourne will design and deliver the upgrades to the City Road northern undercroft by end of 2023-2024 and advocate for the full delivery of upgrades to the City Road East and West. | Deliver Advocate | Delayed |
| Adopt in 2021-22 and then implement an Inclusive Melbourne Strategy that will increase access to opportunities for all people who live, work, study in and visit the city. | Deliver | On track |
| We will be a leading organisation on equality and inclusion and deliver programs in communities that will reduce physical and psychological harm to all people. | Deliver | Completed |
| We will continue to work with Victoria Police and other agencies to deliver a range of initiatives that improve safety on the streets of Melbourne and within our communities. | Partner Deliver | On track |
| Deliver and maintain a clean city through the Rapid Response Clean Team initiative. | Deliver | On track |
| Engage and prepare residents and communities to enhance their resilience to hazards, disasters and the health impacts of climate change. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of people who report feeling safe in the city. | 90% by day, 65% by night |
| Melburnians’ self-reported sense of belonging to community. | At least 70 /100 |
| Rate of recorded family violence incidents. | Decrease |
| Complaints of discrimination based on sexual orientation, sexuality, disability, sex, gender, race, religious or political beliefs or other grounds for unlawful discrimination. | Decrease |
| Proportion of adults who get adequate physical exercise. | Increase |
| Rate of ambulance attendance for alcohol and drug misuse in the municipality. | Decrease |
| Number of transport related injuries and fatalities. | Decrease |
| Proportion of trips made by public transport, bicycle or on foot. | Increase |

https://www.melbourne.vic.gov.au/business/Pages/business-concierge-service.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/Pages/economic-development-strategy-2031.aspx

https://www.melbourne.vic.gov.au/arts-and-culture/strategies-support/funding/Pages/event-partnership-program.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/Pages/united-nations-sustainable-development-goals.aspx

https://participate.melbourne.vic.gov.au/greenline/implementation-plan-overview

https://www.melbourne.vic.gov.au/qvmrenewal

https://participate.melbourne.vic.gov.au/arden/plan

https://participate.melbourne.vic.gov.au/macaulay-refresh

https://www.fishermansbend.vic.gov.au

https://participate.melbourne.vic.gov.au/city-river-strategy

https://participate.melbourne.vic.gov.au/design-excellence-program

https://www.melbourne.vic.gov.au/community/greening-the-city/urban-forest/pages/urban-forest-strategy.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/eco-city/climate-change/Pages/taking-action-climate-change.aspx?k=climate+and+biodiversity+emergency&type=web

https://participate.melbourne.vic.gov.au/disability-access-plan

https://www.melbourne.vic.gov.au/parking-and-transport/transport-planning-projects/Pages/transport-strategy.aspx

https://participate.melbourne.vic.gov.au/inclusive-melbourne-strategy