Council Plan 2021-25 
quarterly report card

October to December 2024

Contents

Economy of the Future	3

Highlights for quarter one (October to December 2024)	3

Our progress	3

The major initiatives we’re delivering this year	4

How we’re measuring progress over four years	5

Melbourne’s unique identity and place	6

Highlights for quarter one (October to December 2024)	6

Our progress	6

The major initiatives we’re delivering this year	8

How we’re measuring progress over four years	9

Aboriginal Melbourne	10

Highlights for quarter one (October to December 2024)	10

Our progress	10

The major initiatives we’re delivering this year	10

How we’re measuring progress over four years	11

Climate and biodiversity emergency	12

Highlights for quarter one (October to December 2024)	12

Our progress	13

The major initiatives we’re delivering this year	14

How we’re measuring progress over four years	15

Access and affordability	16

Highlights for quarter one (October to December 2024)	16

Our progress	16

The major initiatives we’re delivering this year	17

How we’re measuring progress over four years	18

Safety and wellbeing	19

Highlights for quarter one (October to December 2024)	19

Our progress	20

The major initiatives we’re delivering this year	20

How we’re measuring progress over four years	21

# Economy of the Future

We will focus on driving economic recovery and creating the conditions for a strong, adaptive, sustainable and thriving future city economy supported by a diverse mix of industries and jobs that provide dignity and opportunity.

## Highlights for quarter one (October to December 2024) The Small Business Grants Program is currently assessing applications, with successful applicants expected to be notified by early 2025 after recommendations are reviewed in February. The development of a new Economic Development Strategy is progressing well, with important groundwork like economic data analysis and stakeholder engagement completed; formal consultations are scheduled for early 2025. A trial program offering paid internships to international students successfully engaged two interns, benefiting over 3,500 students, and is now undergoing evaluation. A campaign called ‘Positioning Melbourne’ has been finalised to promote the city as a leader in liveability and innovation, set to launch in February 2025. The construction of separated bike lanes on Arden Street has been completed, with work soon beginning on extending these lanes to Moonee Ponds Creek. Development Victoria has released a vision for revitalising Central Pier, which was created through community engagement and emphasises cultural and creative priorities for the area. Representatives strengthened ties with Guangzhou at the World Urban Forum while successful cultural events highlighted connections with China, promoting cross-cultural understanding. Plans are underway for the 2025 Melbourne-Bandung Food Waste Challenge, which aims to create scalable solutions for reducing food waste. Management is preparing to launch an enhanced Melbourne Migrapreneurs Program in early 2025, building on the success of a previous pilot program. The Business Event Sponsorship Program received 80 applications, with 22 selected for funding to support local events and initiatives. The Small Business Grants Program received significant interest with 370 applications totalling $7.88 million in requests across four streams.. ## Our progress With central pier being a state-owned asset, there will be limited ability for the City of Melbourne to influence the outcome of Development Victoria’s "Revitalising Central Pier Waterfront - Vision and Place Principles". Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Continue to strengthen Melbourne’s economic recovery, including through precinct and shopfront activation, delivery of an enhanced business concierge service and support for the night-time economy. | Deliver | On track |
| Ensure Melbourne is the easiest place to start and grow a business through the establishment of Invest Melbourne. | Deliver | Completed |
| Drive economic growth and resilience by implementing the Economic Development Strategy, focusing support on existing and emerging industry sectors. | Deliver Partner | On track |
| Work in partnership with the Victorian Government and other stakeholders to advocate for and deliver integrated high-quality public and active transport in urban renewal areas. | Partner | On track |
| Establish a new tourism entity called Visit Melbourne and review and refresh the program of City of Melbourne-owned and sponsored events to maximise opportunities to drive visitation and spend. | Deliver Partner | Completed |
| Market and promote Melbourne as a great place to live for all, while ensuring key workers have access to affordable housing. | Deliver | Completed |
| Increase visitation to Docklands by partnering with the Victorian Government and key stakeholders to enable reconstruction and redevelopment in Central Pier and surrounds. | Partner Advocate | On track |
| Review Melbourne’s international relationships to optimise future and existing partnerships to enable mutual growth and opportunity. | Deliver | On track |
| Partner with industry to support the development of globally competitive innovation ecosystems. | Partner Deliver | On track |
| Develop a corporate strategy for the City of Melbourne to drive exemplary customer service, digitise services and operations, improve productivity and identify new revenue opportunities. | Deliver | On track |
| Embed the Sustainable Development Goals in the way City of Melbourne plans, prioritises its investments, reports and benchmarks against other cities. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Capital city gross local product. | Increase |
| Number of businesses in the municipality. | Increase |
| Number of start-ups in the municipality. | Increase |
| Vacancy rate of retail premises. | Decrease |
| Proportion of residents employed in the municipality. | Increase |
| Gross local product per capita per person employed. | Increase |
| Number of jobs in the municipality. | Increase |
| Number of visitors to the municipality. | Increase |
| Planning applications decided within required timeframes. | 100% |

# Melbourne’s unique identity and place

Over the next four years we will celebrate and protect the places, people and cultures that make Melbourne a unique, vibrant and creative city with world-leading liveability.

## Highlights for quarter one (October to December 2024) A Cultural Heritage Management Plan and Cultural Values Assessment for Greenline are now complete. Planning is underway for procurement and development of an integrated Cultural Curatorial Framework to enable a First Nations-led (Wurundjeri Woi-wurrung) approach to commissioning creative practitioners for integrated interpretive elements and public art along the length of the north bank. The public review of the Gurrowa Place Controlled Action’s Environmental Report has concluded, and community feedback will shape the final report to be submitted to environmental authorities. Community engagement is in the works for a new Market Square, inviting public input on how this central space can best serve the community. Tram tracks and paving have been removed and natural turf has been installed as a temporary measure in preparation for construction of the Swanston Street Triangle landscape in mid-2025. The Arden Street protected bike lanes have been completed between Wreckyn and Dryburgh streets, with construction soon to commence from Dryburgh Street to Moonee Ponds Creek. The Design Excellence Advisory Committee reviewed the approach to Places for People, an acclaimed 30-year longitudinal study of city life. The Melbourne Design Review Panel provided advice on the draft concept design for Chelmsford Street Open Space. Planning is underway for The Excellent City Series at MPavilion - dynamic conversations with industry and community, that seek to collectively define what Design Excellence means for a diverse and inclusive Melbourne.. ## Our progress Challenges facing the construction sector due to rising costs continue to impact delivery timelines for the Queen Victoria Market Precinct Renewal. Delivery of our major initiatives within the Council Plan term is on track

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Partner with the Victorian Government and other stakeholders to deliver specific components of Greenline along the north bank of the Yarra River. | Deliver Partner | On track |
| Protect Queen Victoria Market as a traditional open-air market. | Deliver | Delayed |
| Deliver Queen Victoria Market6 precinct improvements and Munro Community Hub. | Deliver Partner | Completed |
| Deliver public art projects that reflect Melbourne’s unique culture and heritage. | Deliver | On track |
| Increase the amount of public open space in the municipality with a focus on areas of greatest need. | Deliver | On track |
| Play a lead role in facilitating the delivery of high-quality and climate adapted urban renewal in Arden and Macaulay, Fishermans Bend, and Docklands in partnership with the Victorian Government. | Partner | On track |
| Facilitate increased investment in unique Melbourne events to further activate and celebrate the city. | Partner | On track |
| Celebrate, partner and advocate for investment in the city’s three key waterways, the Yarra River-Birrarung, the Maribyrnong and Moonee Ponds Creek. | Partner Advocate | On track |
| Adopt the Municipal Planning Strategy in 2022-23. | Partner | On track |
| Complete heritage reviews and implement associated planning scheme amendments to protect and celebrate heritage in our municipality. | Deliver | Delayed |
| Champion high quality development and public realm design through delivering the Design Excellence Program. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of residents within 300m of public open space. | Increase |
| Proportion of people surveyed who visit a park in the municipality on a regular basis. | Increase |
| Area of new public open space in Southbank. | 1.1ha (by 2025) |
| Neighbourhoods in the municipality with up-to-date local heritage studies and controls. | 100% |
| Proportion of people who support the city being made up of different cultures. | 100% |
| Value of the creative sector to the local economy. | Increase |
| The number of creative spaces in the municipality. | Increase |
| The number of artists supported by City of Melbourne through city planning, design and city operations. | Increase |
| The number of design reviews of major projects. | Increase |

# Aboriginal Melbourne

For the Wurundjeri, Bunurong, Taungurung, Dja Dja Wurrung and Wadawurrung peoples of the Eastern Kulin, the place now known as Melbourne has always been an important meeting place and location for events of political, cultural, social and educational significance. Over the next four years, we will ensure that First Peoples’ culture, lore, knowledge, and heritage enrich the city’s growth and development.

## Highlights for quarter one (October to December 2024) Work is on the Stolen Generations Marker, with the artist refining the design and creating prototypes. With an activation planned at this site for Moomba. Aboriginal Melbourne is teaming up with Blak & Bright to hold a truth-telling event in March 2025, with plans already started for an event at MPavilion. As part of the Mapping Aboriginal Melbourne initiative, we are in the late stages of hiring a consultant to develop educational resources, with a target completion date of January 2025. Initial discussions about these resources have already taken place with Wurundjeri Woi-wurrung Cultural Heritage Aboriginal Corporation and the Bunurong Land Council, and more meetings with the consultant are scheduled. We are also continuing conversations with the Wurundjeri Woi-wurrung Cultural Heritage Aboriginal Corporation and the Bunurong Land Council to create a memorandum of understanding. The initial part of the First Nations Governance Framework, which focuses on engaging with Traditional Owners and the Aboriginal community, has been completed with work progressing on a comprehensive triage system for the City of Melbourne. ## Our progress Due to competing demands on Traditional Owner time, the development of a partnership will take longer than anticipated with Wurundjeri. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Explore and deliver opportunities for ‘truth-telling’ to facilitate learning, healing, and change within Melbourne and beyond. This will be an opportunity to impart knowledge of thousands of years of rich history, language and stories, as well as provide a form of restorative justice by acknowledging Aboriginal peoples’ experiences of dispossession and inequity. | Partner | On track |
| Implement the Declaration of Recognition and Commitment in good faith which signals and elevates the City of Melbourne’s shared commitment for reconciliation across the whole of the organisation. | Deliver | Completed |
| Govern with Sovereign First Nations to enable true self-determination, where deliberative engagement is proactive, responsive and consistent. | Deliver | Delayed |
| Commence planning for a co-designed First Nations Cultural Precinct with First Peoples – a place to retain, maintain and recreate in a culturally specific geography, where First Peoples can practice continuity of customs and traditions, through uninterrupted connection to lands and waters. | Partner | Closed |
| Support a partnership forum – an annual gathering of the Eastern Kulin (noting the history of Tanderrum). | Partner | Closed |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of people surveyed who demonstrate an understanding of Melbourne’s Aboriginal heritage and culture. | 100% |
| Proportion of people surveyed who believe the relationship with Aboriginal people is important. | 100% |
| Delivery of the City of Melbourne’s Reconciliation Action Plan. | 100% |
| Level of involvement of Traditional Custodians in city governance. | Increase |

# Climate and biodiversity emergency

Over the next four years, we will prioritise our environment and take urgent action to reduce emissions and waste in order to protect public health, strengthen the economy and create a city that mitigates and adapts to climate change. The City of Melbourne declared a climate and biodiversity emergency in 2019.

## Highlights for quarter one (October to December 2024) The Youth Climate Action Grants we completed, which funded various projects led by young people, helping them take action on climate issues. The Melbourne Climate Network has now grown to over 500 members and has connected more than 100 local climate solution providers, enhancing collaboration in our community. The Retrofit Melbourne Plan is in action, featuring discussions on improving energy efficiency and a campaign to encourage less travel for our residents. Preparations for next year’s tree planting season has begun as this year wraps up, with ongoing planning for new tree sites and community engagement. The pilot program for food waste in high-rise buildings is successfully diverting significant amounts from landfills, with new dehydrators installed across the city. In December we launched a fun social media campaign to teach everyone what can and can’t be recycled during the holiday season, helping to reduce waste. The design for an appropriate glass recycling service for the City of Melbourne is complete. The implementation plan for the roll-out of stage one was completed December 2024 that includes access to a glass service for all single-unit dwellings and low-rise multi-unit dwellings that currently receive a FOGO service. Community education programs to occur mid 2025. Going Circular, previously Go Full Circle ran over four weeks from 7 to 30 October. In total four workshops and four live interviews were hosted by Circulise, the delivery partner. Seven City of Melbourne businesses participated in the program, including City Compost Network, Curate Space and Karlaidlaw ## Our progress New building permit requirements related to safety placed on batteries in mid 2024 have delayed commissioning works. The delay of the community energy upgrade fund (CEUF) announcement has impacted the timeline for electrification of a number of City of Melbourne assets. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| To enhance Melbourne’s position as a global leader on climate action, we will undertake bold advocacy on behalf of our community. | Deliver | On track |
| Create an enabling environment for Melbourne businesses and universities to become the employment centre of a resilient zero-carbon economy. | Deliver | On track |
| Progress a planning scheme amendment to improve the environmental performance of buildings in order to reduce emissions to zero by 2040. | Deliver Partner | On track |
| Deliver on our Urban Forest Strategy including tree canopy, private greening incentives and city greening. | Partner | On track |
| Lead the reduction of food waste and diversion of waste from landfill, by continuing the Food Organics, Green Organics rollout through high-rise apartment innovation and by addressing food-waste reduction. | Deliver Partner | On track |
| Support the development of a circular economy through bold leadership and community neighbourhood projects, including the container deposit scheme, alternative waste technologies, circular economy guidelines and partnered or aggregated demand to stimulate end markets. | Deliver | On track |
| Support the development of battery storage and renewable energy in the municipality through the Power Melbourne initiative. | Partner Advocate | Delayed |
| Implement the Climate and Biodiversity Emergency action plan. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Municipal greenhouse gas emissions. | 33% reduction (from 2015 baseline by 2025) |
| On-road transport emissions. | Decrease |
| Installed battery storage capacity in the municipality. | Increase |
| Household waste produced. | 10% reduction (by 2025) |
| Municipal waste diverted from landfill. | 50% increase (by 2025) |
| Alternative water use. | Increase |
| Stormwater quality. | Increase |
| Hospital admissions in relation to extreme weather events. | Decrease |
| Percentage of tree canopy cover in the public realm. | 27% (by 2025) |
| Number of trees planted in the municipality. | 2400 plus number of trees removed in previous year, or 3000, whichever is more. |
| Area of native understorey habitat in the public realm. | Increase |

# Access and affordability

Over the next four years, we will reduce economic and social inequality by ensuring universal access to housing, core services and information.

## Highlights for quarter one (October to December 2024) The new Docklands Farmers Market commenced in December and offered fresh and nutritious food sourced from our local food bowl, (farmers of Victoria), with 40 stall holders participating. This project is managed by the Docklands Chamber of Commerce and run by the Victorian Farmers Market Association in collaboration with the newly established Community 3008 Group in Docklands. Pedestrian activity increased by 540%. The market will be held on the first Sunday of each month over the next 12 months. Two Foodbank Farms to Families events were held in October and November with a total of 580 community members receiving a share in 4,340kg of fresh produce. 65% of those that attended identified as being a City of Melbourne resident. Any left-over produce was boxed up, and redistributed to food relief charities across Melbourne, who are feeding community who are food insecure. City of Melbourne have engaged with food charity van providers who are based at the Queen Victoria Market nightly and provide food to community who are food insecure. The goal is to understand who these providers are and encourage positive relationships with City of Melbourne. The Neighbourhood Volunteer Program has been launched to support underrepresented community members in participating in civic life and addressing local priorities. There were 74 expressions of interest received for the volunteer program, with 22 participants completing phase 1 across seven learning days. The Make Room project achieved practical completion. An opening event was held on December 9, 2024, with residents expected to move in January 2025. Over 350 stakeholders attended tours following the opening. An Aboriginal Community Controlled Organisation commenced operating to deliver homelessness support for people identifying as Aboriginal and/ or Torres Strait Islander in the CBD. Phase 2 of community engagement on the proposed draft concept design for the North Melbourne Community Hub closed in December. Consultation was focused on understanding the communities preference on proposed materials for the new hub, preferred operational models, service delivery and programming, and the structure and flexibility of spaces within the hub.. ## Our progress Further work is being undertaken on the future approach to service planning for City of Melbourne core services under the corporate strategy. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Increase and upgrade accessible, inclusive spaces for women in City of Melbourne sports facilities | Deliver | On track |
| Implement a neighbourhood model by working with communities to develop neighbourhood plans and neighbourhood service centres that respond to the local community’s existing and projected needs. | Deliver | On track |
| Deliver a revitalised library network, including pop-up libraries, to increase access for our diverse community and to help revitalise the city. | Deliver | On track |
| Deliver the Disability Access Plan 2020–2024 including ensuring our services and events are more accessible, increasing the number of accessible adult change facilities, and partnering with community and transport groups to make transport more accessible. | Deliver Partner | Completed |
| Develop and deliver initiatives and programs that will provide food relief to vulnerable members of our community and improve local food production by supporting communities to grow their own food. | Deliver Partner Advocate | Delayed |
| As part of a new corporate strategy for the City of Melbourne, ensure our core services remain accessible and affordable. | Deliver | Delayed |
| In partnership with the Victorian Government commence construction on a replacement North Melbourne Community Centre precinct for the Melrose St community and growing Macaulay population. | Deliver Partner | On track |
| Deliver programs that will build digital literacy skills and capabilities, improve access to free Wi-Fi from our community facilities and advocate for appropriate digital infrastructure, to improve digital inclusion for all, particularly for vulnerable groups. | Deliver | On track |
| Create a new entity ‘Homes Melbourne’, to coordinate and facilitate more affordable housing for key workers and people on low-incomes and progress a demonstration project on Council-owned land, support the Make Room accommodation project and new homeless support hubs for vulnerable citizens to access essential support. | Partner | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Number of people sleeping rough who have not been offered accommodation. | Zero |
| Number of people supported through a range of accommodation including long-term supportive housing and affordable housing. | 500 (by 2025) |
| Number of new demonstration social and affordable housing units facilitated on City of Melbourne land. | 100 (by 2025) |
| Proportion of people reporting food insecurity. | 25% reduction (by 2025) |
| Proportion of people surveyed who participate in lifelong learning in the municipality. | Increase |
| Proportion of people surveyed who participate in arts and cultural activities in the municipality. | Increase |

# Safety and wellbeing

Over the next four years, we will plan and design for the safety and wellbeing of those who live, visit, work and do business in Melbourne, regardless of their background.

## Highlights for quarter one (October to December 2024) Biketober 2024 has concluded. 132 workplaces registered and logged a ride, up from 77 workplaces who participated in 2023. 412,000km were logged by 1785 riders participating through a workplace located in the City of Melbourne. The Rapid Response Clean team have removed 1,602 Tonnes of waste and 33,600 square meters of graffiti. The 555 Flinders St graffiti removal and prevention project was completed in early December. This project was the largest scale removal and prevention project to date. Since completion the site has remained free of graffiti. There have only been two incidents of small tagging at lower levels which were removed within hours. High access graffiti removal works within the Central City continued within the last quarter with over 80 square metres of high access graffiti removed. Anti-graffiti coatings were applied to the recently completed bluestone amphitheatre in Dodds St Southbank in November. City of Melbourne Christmas decorations such as the nutcracker statues were treated with anti-graffiti coatings in late November to ensure any tagging on these assets could be removed immediately without damaging the assets. After successfully reaching a trial service agreement with Metro Trains, the first large scale cleaning and graffiti removal from the Flinders St Station facade (west) has been completed. The station facade on the Flinders St side (from Swanston St to Banana Alley) has been cleaned of dirt, grime and graffiti. This includes the large Yarra Trams substation opposite Queen St. Community Cool Places and Services Grants have been awarded to 7 organisations to provide cool places and services during severe and extreme heat events this summer. Rising Resilience: a six-month program to support community-led resilience in high density living has been developed in partnership with Centre for Public Impact. 15 Resilience Champions participated in workshops in November and December. The Champions are mentored and supported by officers to deliver small scale, local resilience actions.. ## Our progress Additional traffic modelling required by the Department of Transport and Plannings has impacted the Hawke Street Linear Park and Spencer Street North Master Plan, which are currently on hold. Delivery of our major initiatives within the Council Plan term is on track.

## The major initiatives we’re delivering this year

| Initiative | Council’s role | Our progress |
| --- | --- | --- |
| Continue to implement the Transport Strategy 2030, including delivery of a protected bike lane network, station precincts, streets for people, safer speed limits, etcetera. | Advocate Partner Deliver | On track |
| Deliver the North and West Melbourne and Docklands Transport and Amenity Program in partnership with the Victorian Government. | Deliver Partner | Delayed |
| City of Melbourne will design and deliver the upgrades to the City Road northern undercroft by end of 2023-2024 and advocate for the full delivery of upgrades to the City Road East and West. | Deliver Advocate | Delayed |
| Adopt in 2021-22 and then implement an Inclusive Melbourne Strategy that will increase access to opportunities for all people who live, work, study in and visit the city. | Deliver | On track |
| We will be a leading organisation on equality and inclusion and deliver programs in communities that will reduce physical and psychological harm to all people. | Deliver | Completed |
| We will continue to work with Victoria Police and other agencies to deliver a range of initiatives that improve safety on the streets of Melbourne and within our communities. | Partner Deliver | On track |
| Deliver and maintain a clean city through the Rapid Response Clean Team initiative. | Deliver | On track |
| Engage and prepare residents and communities to enhance their resilience to hazards, disasters and the health impacts of climate change. | Deliver | On track |

## How we’re measuring progress over four years

| Indicator | Target outcome |
| --- | --- |
| Proportion of people who report feeling safe in the city. | 90% by day, 65% by night |
| Melburnians’ self-reported sense of belonging to community. | At least 70 /100 |
| Rate of recorded family violence incidents. | Decrease |
| Complaints of discrimination based on sexual orientation, sexuality, disability, sex, gender, race, religious or political beliefs or other grounds for unlawful discrimination. | Decrease |
| Proportion of adults who get adequate physical exercise. | Increase |
| Rate of ambulance attendance for alcohol and drug misuse in the municipality. | Decrease |
| Number of transport related injuries and fatalities. | Decrease |
| Proportion of trips made by public transport, bicycle or on foot. | Increase |

https://www.melbourne.vic.gov.au/business/Pages/business-concierge-service.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/Pages/economic-development-strategy-2031.aspx

https://www.melbourne.vic.gov.au/arts-and-culture/strategies-support/funding/Pages/event-partnership-program.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/Pages/united-nations-sustainable-development-goals.aspx

https://participate.melbourne.vic.gov.au/greenline/implementation-plan-overview

https://www.melbourne.vic.gov.au/qvmrenewal

https://participate.melbourne.vic.gov.au/arden/plan

https://participate.melbourne.vic.gov.au/macaulay-refresh

https://www.fishermansbend.vic.gov.au

https://participate.melbourne.vic.gov.au/city-river-strategy

https://participate.melbourne.vic.gov.au/design-excellence-program

https://www.melbourne.vic.gov.au/community/greening-the-city/urban-forest/pages/urban-forest-strategy.aspx

https://www.melbourne.vic.gov.au/about-council/vision-goals/eco-city/climate-change/Pages/taking-action-climate-change.aspx?k=climate+and+biodiversity+emergency&type=web

https://participate.melbourne.vic.gov.au/disability-access-plan

https://www.melbourne.vic.gov.au/parking-and-transport/transport-planning-projects/Pages/transport-strategy.aspx

https://participate.melbourne.vic.gov.au/inclusive-melbourne-strategy